## Group-Project_WS25-26
Create professional Gantt charts in GanttPRO in a few clicks
Group-Project_WS25-26 | [11 empty] | 2025-10-26 15:41
Color | WBS Number |  |  |  | Task name / Title | Assigned to | Planned start date | Planned end date | Deadline | Progress (%) | Duration (hours) | Estimated hours | Time log (minutes) | Status | Priority | Task description | Predecessor | Budget | Actual cost | Created | Creator | Type | Project | Level
| 1 | Concept Design |  |  |  |  | 2025-10-05 | 2025-10-28 |  | 0 | 552 | 939 | 0 |  |  |  |  | 0 | 0 | 2025-10-21 01:44 | Justin Chin Cheong | project | Group-Project_WS25-26 | 1
| 1.1 |  | Project Plan |  |  |  | 2025-10-05 | 2025-10-14 |  | 0 | 216 | 216 | 0 |  |  |  |  | 0 | 0 | 2025-10-21 01:34 | Justin Chin Cheong | tasks group | Group-Project_WS25-26 / Concept Design | 2
| 1.1.1 |  |  | Breakdown all deliverables and identify sequence |  | Justin Chin Cheong, Okan Can Meral, Ahmad Zeaiter, Abhinav Kothari, Wassi | 2025-10-05 | 2025-10-09 |  | 0 | 96 | 96 | 0 | Open | Medium |  |  | 0 | 0 | 2025-10-21 01:34 | Justin Chin Cheong | task | Group-Project_WS25-26 / Concept Design / Project Plan | 3
| 1.1.2 |  |  | Create Responsibility assignment matrices |  | Justin Chin Cheong | 2025-10-09 | 2025-10-10 |  | 0 | 24 | 24 | 0 | Open | Medium |  | 1.1.1 | 0 | 0 | 2025-10-21 01:34 | Justin Chin Cheong | task | Group-Project_WS25-26 / Concept Design / Project Plan | 3
| 1.1.3 |  |  | Draft a schedule |  | Justin Chin Cheong | 2025-10-10 | 2025-10-12 |  | 0 | 48 | 48 | 0 | Open | Medium |  | 1.1.2 | 0 | 0 | 2025-10-21 01:34 | Justin Chin Cheong | task | Group-Project_WS25-26 / Concept Design / Project Plan | 3
| 1.1.4 |  |  | Create Gantt chart |  | Justin Chin Cheong | 2025-10-12 | 2025-10-13 |  | 0 | 24 | 24 | 0 | Open | Medium |  | 1.1.3 | 0 | 0 | 2025-10-21 01:34 | Justin Chin Cheong | task | Group-Project_WS25-26 / Concept Design / Project Plan | 3
| 1.1.5 |  |  | Approve of Project Plan |  | Justin Chin Cheong, Okan Can Meral, Ahmad Zeaiter, Abhinav Kothari, Wassi | 2025-10-13 | 2025-10-14 |  | 0 | 24 | 24 | 0 | Open | Medium |  | 1.1.4 | 0 | 0 | 2025-10-21 01:34 | Justin Chin Cheong | task | Group-Project_WS25-26 / Concept Design / Project Plan | 3
| 1.2 |  | Market Analysis |  |  |  | 2025-10-13 | 2025-10-18 |  | 0 | 120 | 114 | 0 |  |  |  |  | 0 | 0 | 2025-10-21 01:34 | Justin Chin Cheong | tasks group | Group-Project_WS25-26 / Concept Design | 2
| 1.2.1 |  |  | Perform preliminary Market Analysis |  | Okan Can Meral | 2025-10-13 | 2025-10-14 |  | 0 | 24 | 24 | 0 | Open | Medium |  | 1.1.5 | 0 | 0 | 2025-10-21 01:34 | Justin Chin Cheong | task | Group-Project_WS25-26 / Concept Design / Market Analysis | 3
| 1.2.2 |  |  | Create Financial Estimates |  | Okan Can Meral | 2025-10-14 | 2025-10-16 |  | 0 | 48 | 48 | 0 | Open | Medium |  | 1.2.1 | 0 | 0 | 2025-10-21 01:34 | Justin Chin Cheong | task | Group-Project_WS25-26 / Concept Design / Market Analysis | 3
| 1.2.3 |  |  | Perform Detailed Market Analysis |  | Okan Can Meral | 2025-10-16 | 2025-10-17 |  | 0 | 24 | 24 | 0 | Open | Medium |  | 1.2.2 | 0 | 0 | 2025-10-21 01:34 | Justin Chin Cheong | task | Group-Project_WS25-26 / Concept Design / Market Analysis | 3
| 1.2.4 |  |  | Approve Market Analysis Report |  | Justin Chin Cheong | 2025-10-17 | 2025-10-18 |  | 0 | 24 | 18 | 0 | Open | Medium |  | 1.2.3 | 0 | 0 | 2025-10-21 01:34 | Justin Chin Cheong | task | Group-Project_WS25-26 / Concept Design / Market Analysis | 3
| 1.3 |  | Overall Product Concept |  |  |  | 2025-10-13 | 2025-10-28 |  | 0 | 360 | 306 | 0 |  |  |  |  | 0 | 0 | 2025-10-21 01:34 | Justin Chin Cheong | tasks group | Group-Project_WS25-26 / Concept Design | 2
| 1.3.1 |  |  | Creating Requirements List |  | Ahmad Zeaiter | 2025-10-13 | 2025-10-14 |  | 0 | 24 | 24 | 0 | Open | Medium |  | 1.1.5 | 0 | 0 | 2025-10-21 01:34 | Justin Chin Cheong | task | Group-Project_WS25-26 / Concept Design / Overall Product Concept | 3
| 1.3.2 |  |  | Abstract the Problem and Identify Functions |  | Justin Chin Cheong, Ahmad Zeaiter | 2025-10-13 | 2025-10-15 |  | 0 | 48 | 48 | 0 | Open | Medium |  | 1.3.1 | 0 | 0 | 2025-10-21 01:34 | Justin Chin Cheong | task | Group-Project_WS25-26 / Concept Design / Overall Product Concept | 3
| 1.3.3 |  |  | Approve Key Functions |  | Wassi | 2025-10-15 | 2025-10-16 |  | 0 | 24 | 24 | 0 | Open | Medium |  | 1.3.2 | 0 | 0 | 2025-10-21 01:34 | Justin Chin Cheong | task | Group-Project_WS25-26 / Concept Design / Overall Product Concept | 3
| 1.3.4 |  |  | Developing Working Structures and Morphological Box |  | Justin Chin Cheong, Ahmad Zeaiter, Abhinav Kothari, Wassi | 2025-10-15 | 2025-10-16 |  | 0 | 24 | 24 | 0 | Open | Medium |  | 1.3.3 | 0 | 0 | 2025-10-21 01:34 | Justin Chin Cheong | task | Group-Project_WS25-26 / Concept Design / Overall Product Concept | 3
| 1.3.4.1 |  |  |  | Adjust Solution according to Market Analysis | Ahmad Zeaiter | 2025-10-17 | 2025-10-18 |  | 0 | 24 | 24 | 0 | Open | Medium |  | 1.2.3, 1.3.4 | 0 | 0 | 2025-10-23 01:49 | Justin Chin Cheong | task | Group-Project_WS25-26 / Concept Design / Overall Product Concept / Developing Working Structures and Morphological Box | 4
| 1.3.4.2 |  |  |  | Adjust Solution according to FMEA | Wassi | 2025-10-25 | 2025-10-26 |  | 0 | 24 | 24 | 0 | Open | Medium |  | 1.6.3, 1.3.4 | 0 | 0 | 2025-10-23 01:52 | Justin Chin Cheong | task | Group-Project_WS25-26 / Concept Design / Overall Product Concept / Developing Working Structures and Morphological Box | 4
| 1.3.5 |  |  | Drawing Concept Sketch |  | Ahmad Zeaiter | 2025-10-18 | 2025-10-22 |  | 0 | 96 | 96 | 0 | Open | Medium |  | 1.3.4.1 | 0 | 0 | 2025-10-21 01:34 | Justin Chin Cheong | task | Group-Project_WS25-26 / Concept Design / Overall Product Concept | 3
| 1.3.6 |  |  | Compile preliminary bill of materials |  | Justin Chin Cheong | 2025-10-26 | 2025-10-27 |  | 0 | 24 | 18 | 0 | Open | Medium |  | 1.3.4.2 | 0 | 0 | 2025-10-21 01:34 | Justin Chin Cheong | task | Group-Project_WS25-26 / Concept Design / Overall Product Concept | 3
| 1.3.7 |  |  | Approve Overall Product Concept |  | Wassi | 2025-10-27 | 2025-10-28 |  | 0 | 24 | 24 | 0 | Open | Medium |  | 1.3.6 | 0 | 0 | 2025-10-21 01:34 | Justin Chin Cheong | task | Group-Project_WS25-26 / Concept Design / Overall Product Concept | 3
| 1.4 |  | Functional Structure |  |  |  | 2025-10-18 | 2025-10-27 |  | 0 | 216 | 87 | 0 |  |  |  |  | 0 | 0 | 2025-10-21 01:34 | Justin Chin Cheong | tasks group | Group-Project_WS25-26 / Concept Design | 2
| 1.4.1 |  |  | Create preliminary product FSD |  | Justin Chin Cheong | 2025-10-18 | 2025-10-21 |  | 0 | 72 | 54 | 0 | Open | Medium |  | 1.3.4.1 | 0 | 0 | 2025-10-21 01:34 | Justin Chin Cheong | task | Group-Project_WS25-26 / Concept Design / Functional Structure | 3
| 1.4.2 |  |  | Adjust FSD according to FMEA |  | Justin Chin Cheong | 2025-10-25 | 2025-10-26 |  | 0 | 24 | 24 | 0 | Open | Medium |  | 1.6.3 | 0 | 0 | 2025-10-23 01:55 | Justin Chin Cheong | task | Group-Project_WS25-26 / Concept Design / Functional Structure | 3
| 1.4.3 |  |  | Approve product FSD |  | Abhinav Kothari | 2025-10-26 | 2025-10-27 |  | 0 | 24 | 9 | 0 | Open | Medium |  | 1.4.2 | 0 | 0 | 2025-10-21 01:34 | Justin Chin Cheong | task | Group-Project_WS25-26 / Concept Design / Functional Structure | 3
| 1.5 |  | Human Machine Interface |  |  |  | 2025-10-21 | 2025-10-27 |  | 0 | 144 | 96 | 0 |  |  |  |  | 0 | 0 | 2025-10-21 01:34 | Justin Chin Cheong | tasks group | Group-Project_WS25-26 / Concept Design | 2
| 1.5.1 |  |  | Create table of I/O Interactions |  | Abhinav Kothari | 2025-10-21 | 2025-10-22 |  | 0 | 24 | 24 | 0 | Open | Medium |  | 1.4.1 | 0 | 0 | 2025-10-21 01:34 | Justin Chin Cheong | task | Group-Project_WS25-26 / Concept Design / Human Machine Interface | 3
| 1.5.2 |  |  | Define and Arrange Control Elements |  | Abhinav Kothari | 2025-10-22 | 2025-10-23 |  | 0 | 24 | 24 | 0 | Open | Medium |  | 1.5.1, 1.3.5 | 0 | 0 | 2025-10-21 01:34 | Justin Chin Cheong | task | Group-Project_WS25-26 / Concept Design / Human Machine Interface | 3
| 1.5.3 |  |  | Adjust HMI according to FMEA |  | Abhinav Kothari | 2025-10-25 | 2025-10-26 |  | 0 | 24 | 24 | 0 | Open | Medium |  | 1.6.3 | 0 | 0 | 2025-10-23 01:56 | Justin Chin Cheong | task | Group-Project_WS25-26 / Concept Design / Human Machine Interface | 3
| 1.5.4 |  |  | Approve HMI |  | Ahmad Zeaiter | 2025-10-26 | 2025-10-27 |  | 0 | 24 | 24 | 0 | Open | Medium |  | 1.5.3 | 0 | 0 | 2025-10-21 01:34 | Justin Chin Cheong | task | Group-Project_WS25-26 / Concept Design / Human Machine Interface | 3
| 1.6 |  | D-FMEA |  |  |  | 2025-10-22 | 2025-10-27 |  | 0 | 120 | 120 | 0 |  |  |  |  | 0 | 0 | 2025-10-21 01:34 | Justin Chin Cheong | tasks group | Group-Project_WS25-26 / Concept Design | 2
| 1.6.1 |  |  | Create Basis for Failure Analysis |  | Wassi | 2025-10-22 | 2025-10-23 |  | 0 | 24 | 24 | 0 | Open | Medium |  | 1.5.2 | 0 | 0 | 2025-10-21 01:34 | Justin Chin Cheong | task | Group-Project_WS25-26 / Concept Design / D-FMEA | 3
| 1.6.2 |  |  | Identify Preliminary Failure Modes |  | Wassi | 2025-10-23 | 2025-10-24 |  | 0 | 24 | 24 | 0 | Open | Medium |  | 1.6.1 | 0 | 0 | 2025-10-21 01:34 | Justin Chin Cheong | task | Group-Project_WS25-26 / Concept Design / D-FMEA | 3
| 1.6.3 |  |  | Create Draft of D-FMEA Table |  | Ahmad Zeaiter, Wassi | 2025-10-23 | 2025-10-24 |  | 0 | 24 | 24 | 0 | Open | Medium |  | 1.6.2 | 0 | 0 | 2025-10-21 01:34 | Justin Chin Cheong | task | Group-Project_WS25-26 / Concept Design / D-FMEA | 3
| 1.6.4 |  |  | Create Final D-FMEA Report |  | Justin Chin Cheong, Abhinav Kothari | 2025-10-25 | 2025-10-26 |  | 0 | 24 | 24 | 0 | Open | Medium |  | 1.6.3 | 0 | 0 | 2025-10-21 01:34 | Justin Chin Cheong | task | Group-Project_WS25-26 / Concept Design / D-FMEA | 3
| 1.6.5 |  |  | Approve D-FMEA Report |  | Okan Can Meral | 2025-10-26 | 2025-10-27 |  | 0 | 24 | 24 | 0 | Open | Medium |  | 1.6.4 | 0 | 0 | 2025-10-21 01:34 | Justin Chin Cheong | task | Group-Project_WS25-26 / Concept Design / D-FMEA | 3
| 1.7 |  | Concept Design Close-out |  |  | Justin Chin Cheong, Okan Can Meral, Ahmad Zeaiter, Abhinav Kothari, Wassi | 2025-10-28 | 2025-10-28 |  | 0 | 0 | 0 | 0 | Open | Medium |  | 1.6.5, 1.2.4, 1.5.4, 1.4.3, 1.3.7 | 0 | 0 | 2025-10-21 01:34 | Justin Chin Cheong | milestone | Group-Project_WS25-26 / Concept Design | 2
| 2 | Product Design |  |  |  |  | 2025-10-29 | 2025-12-02 |  | 0 | 816 | 2343.34 | 0 |  |  |  |  | 0 | 0 | 2025-10-21 01:34 | Justin Chin Cheong | project | Group-Project_WS25-26 | 1
| 2.1 |  | Complete 3D Model |  |  |  | 2025-10-29 | 2025-12-02 |  | 0 | 816 | 722.67 | 0 |  |  |  |  | 0 | 0 | 2025-10-21 01:34 | Justin Chin Cheong | tasks group | Group-Project_WS25-26 / Product Design | 2
| 2.1.1 |  |  | Design the Housing and Internal Structure |  | Ahmad Zeaiter | 2025-10-29 | 2025-11-19 |  | 0 | 504 | 504 | 0 | Open | Medium |  | 1.7 | 0 | 0 | 2025-10-21 01:34 | Justin Chin Cheong | task | Group-Project_WS25-26 / Product Design / Complete 3D Model | 3
| 2.1.2 |  |  | Approve of General Structure |  | Wassi | 2025-11-19 | 2025-11-20 |  | 0 | 24 | 24 | 0 | Open | Medium |  | 2.1.1 | 0 | 0 | 2025-10-21 01:34 | Justin Chin Cheong | task | Group-Project_WS25-26 / Product Design / Complete 3D Model | 3
| 2.1.3 |  |  | Integrate PCB and Connectors into 3D Model |  | Ahmad Zeaiter, Wassi | 2025-11-20 | 2025-11-22 |  | 0 | 48 | 48 | 0 | Open | Medium |  | 2.3.5, 2.1.2 | 0 | 0 | 2025-10-21 01:34 | Justin Chin Cheong | task | Group-Project_WS25-26 / Product Design / Complete 3D Model | 3
| 2.1.4 |  |  | Perform Assembly & Interference Check |  | Ahmad Zeaiter | 2025-11-22 | 2025-11-24 |  | 0 | 48 | 48 | 0 | Open | Medium |  | 2.1.3 | 0 | 0 | 2025-10-21 01:34 | Justin Chin Cheong | task | Group-Project_WS25-26 / Product Design / Complete 3D Model | 3
| 2.1.5 |  |  | Adjust 3D Model based on results of Assembly test |  | Ahmad Zeaiter | 2025-11-24 | 2025-11-25 |  | 0 | 24 | 24 | 0 | Open | Medium |  | 2.1.4 | 0 | 0 | 2025-10-23 02:44 | Justin Chin Cheong | task | Group-Project_WS25-26 / Product Design / Complete 3D Model | 3
| 2.1.6 |  |  | Assign Material |  | Ahmad Zeaiter | 2025-11-25 | 2025-11-26 |  | 0 | 24 | 2.67 | 0 | Open | Medium |  | 2.1.5 | 0 | 0 | 2025-10-21 01:34 | Justin Chin Cheong | task | Group-Project_WS25-26 / Product Design / Complete 3D Model | 3
| 2.1.7 |  |  | Adjust 3D Model According to Manufacturability |  | Ahmad Zeaiter, Wassi | 2025-11-28 | 2025-11-29 |  | 0 | 24 | 24 | 0 | Open | Medium |  | 2.1.6, 2.4.3 | 0 | 0 | 2025-10-23 02:50 | Justin Chin Cheong | task | Group-Project_WS25-26 / Product Design / Complete 3D Model | 3
| 2.1.8 |  |  | Adjust 3D Model According to Part Availability |  | Okan Can Meral, Ahmad Zeaiter | 2025-11-29 | 2025-11-30 |  | 0 | 24 | 24 | 0 | Open | Medium |  | 2.1.7, 2.5.2 | 0 | 0 | 2025-10-23 03:00 | Justin Chin Cheong | task | Group-Project_WS25-26 / Product Design / Complete 3D Model | 3
| 2.1.9 |  |  | Approve 3D Model |  | Wassi | 2025-12-01 | 2025-12-02 |  | 0 | 24 | 24 | 0 | Open | Medium |  | 2.1.8 | 0 | 0 | 2025-10-21 01:34 | Justin Chin Cheong | task | Group-Project_WS25-26 / Product Design / Complete 3D Model | 3
| 2.2 |  | Measurement Chain |  |  |  | 2025-10-29 | 2025-11-11 |  | 0 | 312 | 544 | 0 |  |  |  |  | 0 | 0 | 2025-10-21 01:34 | Justin Chin Cheong | tasks group | Group-Project_WS25-26 / Product Design | 2
| 2.2.1 |  |  | Identify necessary Signal Conditioning |  | Justin Chin Cheong | 2025-10-29 | 2025-10-30 |  | 0 | 24 | 24 | 0 | Open | Medium |  | 1.7 | 0 | 0 | 2025-10-21 01:34 | Justin Chin Cheong | task | Group-Project_WS25-26 / Product Design / Measurement Chain | 3
| 2.2.2 |  |  | Design Schematics for Signal Condition |  | Justin Chin Cheong | 2025-10-30 | 2025-11-03 |  | 0 | 96 | 352 | 0 | Open | Medium |  | 2.2.1 | 0 | 0 | 2025-10-21 01:34 | Justin Chin Cheong | task | Group-Project_WS25-26 / Product Design / Measurement Chain | 3
| 2.2.3 |  |  | Adjust Signal Conditioning according to Feedback from Circuit Design |  | Justin Chin Cheong, Wassi | 2025-11-06 | 2025-11-08 |  | 0 | 48 | 48 | 0 | Open | Medium |  | 2.3.3 | 0 | 0 | 2025-10-21 01:34 | Justin Chin Cheong | task | Group-Project_WS25-26 / Product Design / Measurement Chain | 3
| 2.2.4 |  |  | Create detailed Measurement Chain FSD |  | Justin Chin Cheong | 2025-11-08 | 2025-11-10 |  | 0 | 48 | 96 | 0 | Open | Medium |  | 2.2.3 | 0 | 0 | 2025-10-21 01:34 | Justin Chin Cheong | task | Group-Project_WS25-26 / Product Design / Measurement Chain | 3
| 2.2.5 |  |  | Approve the Measurement Chain Design |  | Abhinav Kothari | 2025-11-10 | 2025-11-11 |  | 0 | 24 | 24 | 0 | Open | Medium |  | 2.2.4 | 0 | 0 | 2025-10-21 01:34 | Justin Chin Cheong | task | Group-Project_WS25-26 / Product Design / Measurement Chain | 3
| 2.3 |  | Circuit Diagram |  |  |  | 2025-10-29 | 2025-12-02 |  | 0 | 816 | 594 | 0 |  |  |  |  | 0 | 0 | 2025-10-21 01:34 | Justin Chin Cheong | tasks group | Group-Project_WS25-26 / Product Design | 2
| 2.3.1 |  |  | Draw Electrical System Block Diagram |  | Wassi | 2025-10-29 | 2025-10-31 |  | 0 | 48 | 48 | 0 | Open | Medium |  | 1.7 | 0 | 0 | 2025-10-21 01:34 | Justin Chin Cheong | task | Group-Project_WS25-26 / Product Design / Circuit Diagram | 3
| 2.3.2 |  |  | Create Draft Circuit Schematic |  | Wassi | 2025-10-31 | 2025-11-04 |  | 0 | 96 | 96 | 0 | Open | Medium |  | 2.3.1 | 0 | 0 | 2025-10-21 01:34 | Justin Chin Cheong | task | Group-Project_WS25-26 / Product Design / Circuit Diagram | 3
| 2.3.3 |  |  | Integrate Signal Processing Schematics |  | Justin Chin Cheong, Wassi | 2025-11-04 | 2025-11-06 |  | 0 | 48 | 48 | 0 | Open | Medium |  | 2.3.2, 2.2.2 | 0 | 0 | 2025-10-23 02:17 | Justin Chin Cheong | task | Group-Project_WS25-26 / Product Design / Circuit Diagram | 3
| 2.3.4 |  |  | Design Detailed Circuit Schematic |  | Abhinav Kothari, Wassi | 2025-11-06 | 2025-11-11 |  | 0 | 120 | 48 | 0 | Open | Medium |  | 2.3.3 | 0 | 0 | 2025-10-21 01:34 | Justin Chin Cheong | task | Group-Project_WS25-26 / Product Design / Circuit Diagram | 3
| 2.3.5 |  |  | Design PCB |  | Abhinav Kothari, Wassi | 2025-11-11 | 2025-11-19 |  | 0 | 192 | 192 | 0 | Open | Medium |  | 2.3.4, 2.2.3 | 0 | 0 | 2025-10-23 02:32 | Justin Chin Cheong | task | Group-Project_WS25-26 / Product Design / Circuit Diagram | 3
| 2.3.6 |  |  | Perform Electrical Safety Checks |  | Wassi | 2025-11-19 | 2025-11-21 |  | 0 | 48 | 48 | 0 | Open | Medium |  | 2.3.5 | 0 | 0 | 2025-10-23 02:39 | Justin Chin Cheong | task | Group-Project_WS25-26 / Product Design / Circuit Diagram | 3
| 2.3.7 |  |  | Adjust PCB according to Manufacturability |  | Wassi | 2025-11-27 | 2025-11-28 |  | 0 | 24 | 24 | 0 | Open | Medium |  | 2.4.3, 2.3.6 | 0 | 0 | 2025-10-23 02:50 | Justin Chin Cheong | task | Group-Project_WS25-26 / Product Design / Circuit Diagram | 3
| 2.3.8 |  |  | Adjust PCB according to Availability |  | Wassi | 2025-11-28 | 2025-11-29 |  | 0 | 24 | 24 | 0 | Open | Medium |  | 2.5.2 | 0 | 0 | 2025-10-23 03:02 | Justin Chin Cheong | task | Group-Project_WS25-26 / Product Design / Circuit Diagram | 3
| 2.3.9 |  |  | Create Final Electrical Documentation Package |  | Wassi | 2025-11-29 | 2025-12-01 |  | 0 | 48 | 48 | 0 | Open | Medium |  | 2.3.7, 2.3.8 | 0 | 0 | 2025-10-21 01:34 | Justin Chin Cheong | task | Group-Project_WS25-26 / Product Design / Circuit Diagram | 3
| 2.3.10 |  |  | Approve Final Circuit Diagram |  | Justin Chin Cheong | 2025-12-01 | 2025-12-02 |  | 0 | 24 | 18 | 0 | Open | Medium |  | 2.3.9, 2.2.5 | 0 | 0 | 2025-10-21 01:34 | Justin Chin Cheong | task | Group-Project_WS25-26 / Product Design / Circuit Diagram | 3
| 2.4 |  | Technology Selection for “Make” Parts |  |  |  | 2025-11-21 | 2025-12-02 |  | 0 | 264 | 242.67 | 0 |  |  |  |  | 0 | 0 | 2025-10-21 01:34 | Justin Chin Cheong | tasks group | Group-Project_WS25-26 / Product Design | 2
| 2.4.1 |  |  | Identify all necessary “make” parts |  | Justin Chin Cheong | 2025-11-21 | 2025-11-22 |  | 0 | 24 | 2.67 | 0 | Open | Medium |  | 2.3.5, 2.1.3 | 0 | 0 | 2025-10-21 01:34 | Justin Chin Cheong | task | Group-Project_WS25-26 / Product Design / Technology Selection for “Make” Parts | 3
| 2.4.2 |  |  | Approve list of “Make” + “Buy” parts |  | Okan Can Meral | 2025-11-23 | 2025-11-24 |  | 0 | 24 | 24 | 0 | Open | Medium |  | 2.4.1, 2.5.1 | 0 | 0 | 2025-10-21 01:34 | Justin Chin Cheong | task | Group-Project_WS25-26 / Product Design / Technology Selection for “Make” Parts | 3
| 2.4.3 |  |  | Assess Manufacturability of Parts |  | Wassi | 2025-11-24 | 2025-11-26 |  | 0 | 48 | 48 | 0 | Open | Medium |  | 2.4.2 | 0 | 0 | 2025-10-21 01:34 | Justin Chin Cheong | task | Group-Project_WS25-26 / Product Design / Technology Selection for “Make” Parts | 3
| 2.4.4 |  |  | Select Manufacturing Process and Materials for each part |  | Wassi | 2025-11-26 | 2025-11-27 |  | 0 | 24 | 24 | 0 | Open | Medium |  | 2.4.3 | 0 | 0 | 2025-10-21 01:34 | Justin Chin Cheong | task | Group-Project_WS25-26 / Product Design / Technology Selection for “Make” Parts | 3
| 2.4.5 |  |  | Approve of material and manufacturing processes of “make” parts |  | Justin Chin Cheong | 2025-11-27 | 2025-11-28 |  | 0 | 24 | 48 | 0 | Open | Medium |  | 2.4.4 | 0 | 0 | 2025-10-21 01:34 | Justin Chin Cheong | task | Group-Project_WS25-26 / Product Design / Technology Selection for “Make” Parts | 3
| 2.4.6 |  |  | Define the Assembly Technology (Area by Area) |  | Justin Chin Cheong, Wassi | 2025-11-28 | 2025-12-01 |  | 0 | 72 | 72 | 0 | Open | Medium |  | 2.4.5 | 0 | 0 | 2025-10-21 01:34 | Justin Chin Cheong | task | Group-Project_WS25-26 / Product Design / Technology Selection for “Make” Parts | 3
| 2.4.7 |  |  | Approve Manufacturing and Assembly Guide Package |  | Okan Can Meral | 2025-12-01 | 2025-12-02 |  | 0 | 24 | 24 | 0 | Open | Medium |  | 2.4.6 | 0 | 0 | 2025-10-21 01:34 | Justin Chin Cheong | task | Group-Project_WS25-26 / Product Design / Technology Selection for “Make” Parts | 3
| 2.5 |  | Requirements Manual for “Buy” Parts |  |  |  | 2025-11-21 | 2025-12-02 |  | 0 | 264 | 240 | 0 |  |  |  |  | 0 | 0 | 2025-10-21 01:34 | Justin Chin Cheong | tasks group | Group-Project_WS25-26 / Product Design | 2
| 2.5.1 |  |  | Identify all necessary “buy” parts |  | Okan Can Meral | 2025-11-21 | 2025-11-22 |  | 0 | 24 | 24 | 0 | Open | Medium |  | 2.1.3, 2.3.5 | 0 | 0 | 2025-10-21 01:34 | Justin Chin Cheong | task | Group-Project_WS25-26 / Product Design / Requirements Manual for “Buy” Parts | 3
| 2.5.2 |  |  | Assess availability of "buy" Parts |  | Okan Can Meral | 2025-11-24 | 2025-11-27 |  | 0 | 72 | 72 | 0 | Open | Medium |  | 2.4.2 | 0 | 0 | 2025-10-21 01:34 | Justin Chin Cheong | task | Group-Project_WS25-26 / Product Design / Requirements Manual for “Buy” Parts | 3
| 2.5.3 |  |  | Create part requirements sheets for each “buy” part |  | Okan Can Meral, Ahmad Zeaiter | 2025-11-27 | 2025-12-01 |  | 0 | 96 | 96 | 0 | Open | Medium |  | 2.5.2 | 0 | 0 | 2025-10-21 01:34 | Justin Chin Cheong | task | Group-Project_WS25-26 / Product Design / Requirements Manual for “Buy” Parts | 3
| 2.5.4 |  |  | Approve requirement sheets |  | Justin Chin Cheong | 2025-12-01 | 2025-12-02 |  | 0 | 24 | 48 | 0 | Open | Medium |  | 2.5.3 | 0 | 0 | 2025-10-21 01:34 | Justin Chin Cheong | task | Group-Project_WS25-26 / Product Design / Requirements Manual for “Buy” Parts | 3
| 2.6 |  | Product Design Close-out |  |  | Justin Chin Cheong, Okan Can Meral, Ahmad Zeaiter, Abhinav Kothari, Wassi | 2025-12-02 | 2025-12-02 |  | 0 | 0 | 0 | 0 | Open | Medium |  | 2.5.4, 2.4.7, 2.3.10, 2.1.9 | 0 | 0 | 2025-10-21 01:34 | Justin Chin Cheong | milestone | Group-Project_WS25-26 / Product Design | 2
| 3 | Project Documentation |  |  |  |  | 2025-10-29 | 2026-01-12 |  | 6 | 1800 | 3535.65 | 0 |  |  |  |  | 0 | 0 | 2025-10-21 01:34 | Justin Chin Cheong | project | Group-Project_WS25-26 | 1
| 3.1 |  | Technical Drawings for Main Assembly |  |  |  | 2025-12-03 | 2026-01-04 |  | 0 | 768 | 441 | 0 |  |  |  |  | 0 | 0 | 2025-10-21 01:34 | Justin Chin Cheong | tasks group | Group-Project_WS25-26 / Project Documentation | 2
| 3.1.1 |  |  | Create Assembly Drawing with Section and Detail Views |  | Ahmad Zeaiter | 2025-12-03 | 2025-12-17 |  | 0 | 336 | 336 | 0 | Open | Medium |  | 2.6 | 0 | 0 | 2025-10-21 01:34 | Justin Chin Cheong | task | Group-Project_WS25-26 / Project Documentation / Technical Drawings for Main Assembly | 3
| 3.1.2 |  |  | Verify drawings for electrical components |  | Wassi | 2025-12-17 | 2025-12-19 |  | 0 | 48 | 48 | 0 | Open | Medium |  | 3.1.1, 3.4.3 | 0 | 0 | 2025-10-21 01:34 | Justin Chin Cheong | task | Group-Project_WS25-26 / Project Documentation / Technical Drawings for Main Assembly | 3
| 3.1.3 |  |  | Verify Compliance with DIN 406 Drawing Standards |  | Abhinav Kothari | 2025-12-20 | 2025-12-22 |  | 0 | 48 | 48 | 0 | Open | Medium |  | 3.1.2 | 0 | 0 | 2025-10-21 01:34 | Justin Chin Cheong | task | Group-Project_WS25-26 / Project Documentation / Technical Drawings for Main Assembly | 3
| 3.1.4 |  |  | Approval of technical drawing |  | Wassi | 2026-01-03 | 2026-01-04 |  | 0 | 24 | 9 | 0 | Open | Medium |  | 3.1.3 | 0 | 0 | 2025-10-21 01:34 | Justin Chin Cheong | task | Group-Project_WS25-26 / Project Documentation / Technical Drawings for Main Assembly | 3
| 3.2 |  | Program Flow Chart |  |  |  | 2025-12-03 | 2025-12-20 |  | 0 | 408 | 267 | 0 |  |  |  |  | 0 | 0 | 2025-10-21 01:34 | Justin Chin Cheong | tasks group | Group-Project_WS25-26 / Project Documentation | 2
| 3.2.1 |  |  | Draw Main structural flowchart |  | Abhinav Kothari | 2025-12-03 | 2025-12-07 |  | 0 | 96 | 33 | 0 | Open | Medium |  | 2.6 | 0 | 0 | 2025-10-21 01:34 | Justin Chin Cheong | task | Group-Project_WS25-26 / Project Documentation / Program Flow Chart | 3
| 3.2.2 |  |  | Draw User interaction flowchart |  | Abhinav Kothari | 2025-12-07 | 2025-12-09 |  | 0 | 48 | 114 | 0 | Open | Medium |  | 3.2.1 | 0 | 0 | 2025-10-21 01:34 | Justin Chin Cheong | task | Group-Project_WS25-26 / Project Documentation / Program Flow Chart | 3
| 3.2.3 |  |  | Draw Calibration menu flowchart |  | Abhinav Kothari | 2025-12-08 | 2025-12-10 |  | 0 | 48 | 48 | 0 | Open | Medium |  | 3.2.2 | 0 | 0 | 2025-10-21 01:34 | Justin Chin Cheong | task | Group-Project_WS25-26 / Project Documentation / Program Flow Chart | 3
| 3.2.4 |  |  | Draw Data handling flowchart |  | Abhinav Kothari | 2025-12-10 | 2025-12-11 |  | 0 | 24 | 24 | 0 | Open | Medium |  | 3.2.3 | 0 | 0 | 2025-10-21 01:34 | Justin Chin Cheong | task | Group-Project_WS25-26 / Project Documentation / Program Flow Chart | 3
| 3.2.5 |  |  | Draw Error and Internal Interrupt handling flowchart |  | Abhinav Kothari | 2025-12-11 | 2025-12-12 |  | 0 | 24 | 24 | 0 | Open | Medium |  | 3.2.4 | 0 | 0 | 2025-10-21 01:34 | Justin Chin Cheong | task | Group-Project_WS25-26 / Project Documentation / Program Flow Chart | 3
| 3.2.6 |  |  | Approve program flowcharts |  | Ahmad Zeaiter | 2025-12-19 | 2025-12-20 |  | 0 | 24 | 24 | 0 | Open | Medium |  | 3.2.5 | 0 | 0 | 2025-10-21 01:34 | Justin Chin Cheong | task | Group-Project_WS25-26 / Project Documentation / Program Flow Chart | 3
| 3.3 |  | Bill of Material |  |  |  | 2025-12-03 | 2026-01-04 |  | 0 | 768 | 390 | 0 |  |  |  |  | 0 | 0 | 2025-10-21 01:34 | Justin Chin Cheong | tasks group | Group-Project_WS25-26 / Project Documentation | 2
| 3.3.1 |  |  | Create master BOM spreadsheet |  | Justin Chin Cheong | 2025-12-03 | 2025-12-04 |  | 0 | 24 | 18 | 0 | Open | Medium |  | 2.6 | 0 | 0 | 2025-10-21 01:34 | Justin Chin Cheong | task | Group-Project_WS25-26 / Project Documentation / Bill of Material | 3
| 3.3.2 |  |  | Itemize all Mechanical Components |  |  | 2025-12-04 | 2025-12-10 |  | 0 | 144 | 126 | 0 |  |  |  |  | 0 | 0 | 2025-10-21 01:34 | Justin Chin Cheong | tasks group | Group-Project_WS25-26 / Project Documentation / Bill of Material | 3
| 3.3.2.1 |  |  |  | Identify norm spec for each standard mechanical component | Justin Chin Cheong | 2025-12-04 | 2025-12-07 |  | 0 | 72 | 54 | 0 | Open | Medium |  | 3.3.1 | 0 | 0 | 2025-10-21 01:34 | Justin Chin Cheong | task | Group-Project_WS25-26 / Project Documentation / Bill of Material / Itemize all Mechanical Components | 4
| 3.3.2.2 |  |  |  | Verify all specifications of all mechanical components | Wassi | 2025-12-07 | 2025-12-10 |  | 0 | 72 | 72 | 0 | Open | Medium |  | 3.3.2.1 | 0 | 0 | 2025-10-21 01:34 | Justin Chin Cheong | task | Group-Project_WS25-26 / Project Documentation / Bill of Material / Itemize all Mechanical Components | 4
| 3.3.3 |  |  | Itemize all Electrical Components |  |  | 2025-12-10 | 2025-12-16 |  | 0 | 144 | 126 | 0 |  |  |  |  | 0 | 0 | 2025-10-21 01:34 | Justin Chin Cheong | tasks group | Group-Project_WS25-26 / Project Documentation / Bill of Material | 3
| 3.3.3.1 |  |  |  | Add technical specs for all electrical components | Justin Chin Cheong | 2025-12-10 | 2025-12-13 |  | 0 | 72 | 54 | 0 | Open | Medium |  | 3.3.2.2 | 0 | 0 | 2025-10-21 01:34 | Justin Chin Cheong | task | Group-Project_WS25-26 / Project Documentation / Bill of Material / Itemize all Electrical Components | 4
| 3.3.3.2 |  |  |  | Verify all specifications of all electrical components | Ahmad Zeaiter | 2025-12-13 | 2025-12-16 |  | 0 | 72 | 72 | 0 | Open | Medium |  | 3.3.3.1 | 0 | 0 | 2025-10-21 01:34 | Justin Chin Cheong | task | Group-Project_WS25-26 / Project Documentation / Bill of Material / Itemize all Electrical Components | 4
| 3.3.4 |  |  | Add cost to all components |  | Justin Chin Cheong | 2025-12-16 | 2025-12-18 |  | 0 | 48 | 48 | 0 | Open | Medium |  | 3.3.3.2 | 0 | 0 | 2025-10-21 01:34 | Justin Chin Cheong | task | Group-Project_WS25-26 / Project Documentation / Bill of Material | 3
| 3.3.5 |  |  | Verify Part Numbers according to Drawings |  | Justin Chin Cheong | 2025-12-20 | 2025-12-22 |  | 0 | 48 | 48 | 0 | Open | Medium |  | 3.1.2 | 0 | 0 | 2025-10-23 14:29 | Justin Chin Cheong | task | Group-Project_WS25-26 / Project Documentation / Bill of Material | 3
| 3.3.6 |  |  | Approve final BOM |  | Abhinav Kothari | 2026-01-03 | 2026-01-04 |  | 0 | 24 | 24 | 0 | Open | Medium |  | 3.3.5 | 0 | 0 | 2025-10-21 01:34 | Justin Chin Cheong | task | Group-Project_WS25-26 / Project Documentation / Bill of Material | 3
| 3.4 |  | Production Planning |  |  |  | 2025-12-03 | 2026-01-08 |  | 0 | 864 | 521.97 | 0 |  |  |  |  | 0 | 0 | 2025-10-21 01:34 | Justin Chin Cheong | tasks group | Group-Project_WS25-26 / Project Documentation | 2
| 3.4.1 |  |  | Estimate Number of Required Machines |  | Wassi | 2025-12-03 | 2025-12-05 |  | 0 | 48 | 48 | 0 | Open | Medium |  | 2.6 | 0 | 0 | 2025-10-21 01:34 | Justin Chin Cheong | task | Group-Project_WS25-26 / Project Documentation / Production Planning | 3
| 3.4.2 |  |  | Estimate Manufacturing and Assembly Time per Part |  | Wassi | 2025-12-05 | 2025-12-11 |  | 0 | 144 | 144 | 0 | Open | Medium |  | 3.4.1 | 0 | 0 | 2025-10-21 01:34 | Justin Chin Cheong | task | Group-Project_WS25-26 / Project Documentation / Production Planning | 3
| 3.4.3 |  |  | Create Assembly Sequence and Flowchart |  | Abhinav Kothari, Wassi | 2025-12-11 | 2025-12-15 |  | 0 | 96 | 96 | 0 | Open | Medium |  | 3.4.2 | 0 | 0 | 2025-10-21 01:34 | Justin Chin Cheong | task | Group-Project_WS25-26 / Project Documentation / Production Planning | 3
| 3.4.4 |  |  | Estimate Workforce Requirements |  | Wassi | 2025-12-15 | 2025-12-17 |  | 0 | 48 | 47.97 | 0 | Open | Medium |  | 3.4.3 | 0 | 0 | 2025-10-21 01:34 | Justin Chin Cheong | task | Group-Project_WS25-26 / Project Documentation / Production Planning | 3
| 3.4.5 |  |  | Optimize Assembly Sequence Costs |  | Abhinav Kothari, Wassi | 2025-12-20 | 2025-12-23 |  | 0 | 72 | 72 | 0 | Open | Medium |  | 3.5.3 | 0 | 0 | 2025-10-23 14:11 | Justin Chin Cheong | task | Group-Project_WS25-26 / Project Documentation / Production Planning | 3
| 3.4.6 |  |  | Approve of Assembly Sequence and Flowchart |  | Justin Chin Cheong | 2026-01-03 | 2026-01-04 |  | 0 | 24 | 18 | 0 | Open | Medium |  | 3.4.5 | 0 | 0 | 2025-10-21 01:34 | Justin Chin Cheong | task | Group-Project_WS25-26 / Project Documentation / Production Planning | 3
| 3.4.7 |  |  | Create Production Planning Summary |  | Wassi | 2026-01-04 | 2026-01-07 |  | 0 | 72 | 72 | 0 | Open | Medium |  | 3.4.6 | 0 | 0 | 2025-10-21 01:34 | Justin Chin Cheong | task | Group-Project_WS25-26 / Project Documentation / Production Planning | 3
| 3.4.8 |  |  | Approve Production Plan |  | Okan Can Meral | 2026-01-07 | 2026-01-08 |  | 0 | 24 | 24 | 0 | Open | Medium |  | 3.4.7 | 0 | 0 | 2025-10-21 01:34 | Justin Chin Cheong | task | Group-Project_WS25-26 / Project Documentation / Production Planning | 3
| 3.5 |  | Cost Calculation |  |  |  | 2025-12-05 | 2026-01-06 |  | 0 | 768 | 474 | 0 |  |  |  |  | 0 | 0 | 2025-10-21 01:34 | Justin Chin Cheong | tasks group | Group-Project_WS25-26 / Project Documentation | 2
| 3.5.1 |  |  | Estimate Fixed Costs |  | Okan Can Meral | 2025-12-05 | 2025-12-11 |  | 0 | 144 | 144 | 0 | Open | Medium |  | 3.4.1 | 0 | 0 | 2025-10-21 01:34 | Justin Chin Cheong | task | Group-Project_WS25-26 / Project Documentation / Cost Calculation | 3
| 3.5.2 |  |  | Estimate Variable Costs |  |  | 2025-12-11 | 2025-12-22 |  | 0 | 264 | 192 | 0 |  |  |  | 3.5.1 | 0 | 0 | 2025-10-21 01:34 | Justin Chin Cheong | tasks group | Group-Project_WS25-26 / Project Documentation / Cost Calculation | 3
| 3.5.2.1 |  |  |  | Perform Initial Variable Cost Estimation | Okan Can Meral | 2025-12-11 | 2025-12-16 |  | 0 | 120 | 120 | 0 | Open | Medium |  | 3.4.2 | 0 | 0 | 2025-10-23 14:19 | Justin Chin Cheong | task | Group-Project_WS25-26 / Project Documentation / Cost Calculation / Estimate Variable Costs | 4
| 3.5.2.2 |  |  |  | Perform Final Variable Cost Estimate | Okan Can Meral | 2025-12-19 | 2025-12-22 |  | 0 | 72 | 72 | 0 | Open | Medium |  | 3.5.2.1, 3.4.4, 3.3.4 | 0 | 0 | 2025-10-23 14:20 | Justin Chin Cheong | task | Group-Project_WS25-26 / Project Documentation / Cost Calculation / Estimate Variable Costs | 4
| 3.5.3 |  |  | Estimate Overheads and Miscellaneous |  | Okan Can Meral | 2025-12-16 | 2025-12-19 |  | 0 | 72 | 72 | 0 | Open | Medium |  | 3.5.2.1 | 0 | 0 | 2025-10-21 01:34 | Justin Chin Cheong | task | Group-Project_WS25-26 / Project Documentation / Cost Calculation | 3
| 3.5.4 |  |  | Summary Costs and Revenue Projection |  | Okan Can Meral | 2026-01-03 | 2026-01-05 |  | 0 | 48 | 48 | 0 | Open | Medium |  | 3.5.2.2, 3.5.3 | 0 | 0 | 2025-10-21 01:34 | Justin Chin Cheong | task | Group-Project_WS25-26 / Project Documentation / Cost Calculation | 3
| 3.5.5 |  |  | Approve Cost Calculation Report |  | Justin Chin Cheong | 2026-01-05 | 2026-01-06 |  | 0 | 24 | 18 | 0 | Open | Medium |  | 3.5.4 | 0 | 0 | 2025-10-21 01:34 | Justin Chin Cheong | task | Group-Project_WS25-26 / Project Documentation / Cost Calculation | 3
| 3.6 |  | Specification sheet |  |  |  | 2025-10-29 | 2026-01-04 |  | 28 | 1608 | 336 | 0 |  |  |  |  | 0 | 0 | 2025-10-21 01:34 | Justin Chin Cheong | tasks group | Group-Project_WS25-26 / Project Documentation | 2
| 3.6.1 |  |  | Outline Functional specifications |  | Abhinav Kothari | 2025-10-29 | 2025-10-31 |  | 0 | 48 | 48 | 0 | Open | Medium |  | 1.7 | 0 | 0 | 2025-10-21 01:34 | Justin Chin Cheong | task | Group-Project_WS25-26 / Project Documentation / Specification sheet | 3
| 3.6.2 |  |  | Outline Physical and Mechanical Specifications |  | Ahmad Zeaiter, Abhinav Kothari | 2025-11-20 | 2025-11-22 |  | 0 | 48 | 48 | 0 | Open | Medium |  | 2.1.2, 3.6.1 | 0 | 0 | 2025-10-21 01:34 | Justin Chin Cheong | task | Group-Project_WS25-26 / Project Documentation / Specification sheet | 3
| 3.6.3 |  |  | Outline Electrical Specifications |  | Abhinav Kothari, Wassi | 2025-11-23 | 2025-11-27 |  | 100 | 96 | 96 | 0 | Done | Medium |  |  | 0 | 0 | 2025-10-21 01:34 | Justin Chin Cheong | task | Group-Project_WS25-26 / Project Documentation / Specification sheet | 3
| 3.6.4 |  |  | Adjust Specification on Final Design |  | Abhinav Kothari | 2025-12-12 | 2025-12-17 |  | 0 | 120 | 120 | 0 | Open | Medium |  | 3.6.3, 3.6.2, 2.6 | 0 | 0 | 2025-10-23 14:55 | Justin Chin Cheong | task | Group-Project_WS25-26 / Project Documentation / Specification sheet | 3
| 3.6.5 |  |  | Approve specifications sheet |  | Justin Chin Cheong | 2026-01-03 | 2026-01-04 |  | 0 | 24 | 24 | 0 | Open | Medium |  | 3.6.4 | 0 | 0 | 2025-10-21 01:34 | Justin Chin Cheong | task | Group-Project_WS25-26 / Project Documentation / Specification sheet | 3
| 3.7 |  | User manual |  |  |  | 2025-11-21 | 2026-01-04 |  | 0 | 1056 | 336 | 0 |  |  |  |  | 0 | 0 | 2025-10-21 01:34 | Justin Chin Cheong | tasks group | Group-Project_WS25-26 / Project Documentation | 2
| 3.7.1 |  |  | Write Safety Disclaimers |  | Justin Chin Cheong | 2025-11-21 | 2025-11-23 |  | 0 | 48 | 48 | 0 | Open | Medium |  | 2.3.6 | 0 | 0 | 2025-10-23 14:53 | Justin Chin Cheong | task | Group-Project_WS25-26 / Project Documentation / User manual | 3
| 3.7.2 |  |  | Write Functional Instructions |  | Okan Can Meral | 2025-12-10 | 2025-12-15 |  | 0 | 120 | 120 | 0 | Open | Medium |  | 3.2.2, 3.7.1 | 0 | 0 | 2025-10-23 14:52 | Justin Chin Cheong | task | Group-Project_WS25-26 / Project Documentation / User manual | 3
| 3.7.3 |  |  | Explain troubleshooting steps |  | Abhinav Kothari | 2025-12-17 | 2025-12-23 |  | 0 | 144 | 144 | 0 | Open | Medium |  | 3.7.2 | 0 | 0 | 2025-10-21 01:34 | Justin Chin Cheong | task | Group-Project_WS25-26 / Project Documentation / User manual | 3
| 3.7.4 |  |  | Approve user manual |  | Ahmad Zeaiter | 2026-01-03 | 2026-01-04 |  | 0 | 24 | 24 | 0 | Open | Medium |  | 3.7.3 | 0 | 0 | 2025-10-21 01:34 | Justin Chin Cheong | task | Group-Project_WS25-26 / Project Documentation / User manual | 3
| 3.8 |  | Interactive brochure |  |  |  | 2025-11-11 | 2026-01-12 |  | 0 | 1488 | 769.68 | 0 |  |  |  |  | 0 | 0 | 2025-10-21 01:34 | Justin Chin Cheong | tasks group | Group-Project_WS25-26 / Project Documentation | 2
| 3.8.1 |  |  | Create first draft of Brochure |  | Justin Chin Cheong, Ahmad Zeaiter, Abhinav Kothari | 2025-11-11 | 2025-12-01 |  | 0 | 480 | 480 | 0 | Open | Medium |  | 1.7 | 0 | 0 | 2025-10-21 01:34 | Justin Chin Cheong | task | Group-Project_WS25-26 / Project Documentation / Interactive brochure | 3
| 3.8.2 |  |  | Create Interactive Media for brochure |  | Justin Chin Cheong, Ahmad Zeaiter, Abhinav Kothari | 2025-12-17 | 2025-12-22 |  | 0 | 120 | 97.68 | 0 | Open | Medium |  | 3.8.1, 2.1.9 | 0 | 0 | 2025-10-21 01:34 | Justin Chin Cheong | task | Group-Project_WS25-26 / Project Documentation / Interactive brochure | 3
| 3.8.3 |  |  | Design Final Brochure |  | Justin Chin Cheong, Ahmad Zeaiter, Abhinav Kothari | 2026-01-04 | 2026-01-11 |  | 0 | 168 | 168 | 0 | Open | Medium |  | 3.8.2 | 0 | 0 | 2025-10-23 14:58 | Justin Chin Cheong | task | Group-Project_WS25-26 / Project Documentation / Interactive brochure | 3
| 3.8.4 |  |  | Approve brochure |  | Okan Can Meral, Wassi | 2026-01-11 | 2026-01-12 |  | 0 | 24 | 24 | 0 | Open | Medium |  | 3.8.3 | 0 | 0 | 2025-10-21 01:34 | Justin Chin Cheong | task | Group-Project_WS25-26 / Project Documentation / Interactive brochure | 3
| 3.9 |  | Project Documentation Closeout |  |  | Justin Chin Cheong, Okan Can Meral, Ahmad Zeaiter, Abhinav Kothari, Wassi | 2026-01-12 | 2026-01-12 |  | 0 | 0 | 0 | 0 | Open | Medium |  | 3.1.4, 3.5.5, 3.4.8, 3.3.6, 3.6.5, 3.7.4, 3.8.4, 3.2.6 | 0 | 0 | 2025-10-21 01:34 | Justin Chin Cheong | milestone | Group-Project_WS25-26 / Project Documentation | 2
| 4 | Project Close-out |  |  |  | Justin Chin Cheong, Okan Can Meral, Ahmad Zeaiter, Abhinav Kothari, Wassi | 2026-01-13 | 2026-01-13 |  | 0 | 0 | 0 | 0 | Open | Medium |  | 3.9 | 0 | 0 | 2025-10-26 01:02 | Justin Chin Cheong | milestone | Group-Project_WS25-26 | 1
This document has been created with the help of https://ganttpro.com online service