## Group-Project_WS25-26
Create professional Gantt charts in GanttPRO in a few clicks
Group-Project_WS25-26 | [8 empty] | 2025-10-25 23:37
| WBS Number | Task name | Assigned to | Start | End | Predecessor | Type
| 1 | Concept Design |  | 2025-10-05 | 2025-10-28 |  | phase
| 1.1 | Project Plan |  | 2025-10-05 | 2025-10-14 |  | deliverable
| 1.1.1 | Breakdown all deliverables and identify sequence | Justin, Okan, Ahmad, Abhinav, Wasim | 2025-10-05 | 2025-10-09 |  | task
| 1.1.2 | Create Responsibility assignment matrices | Justin | 2025-10-09 | 2025-10-10 | 1.1.1 | task
| 1.1.3 | Draft a schedule | Justin | 2025-10-10 | 2025-10-12 | 1.1.2 | task
| 1.1.4 | Create Gantt chart | Justin | 2025-10-12 | 2025-10-13 | 1.1.3 | task
| 1.1.5 | Approve of Project Plan | Justin, Okan, Ahmad, Abhinav, Wasim | 2025-10-13 | 2025-10-14 | 1.1.4 | task
| 1.2 | Market Analysis |  | 2025-10-13 | 2025-10-18 |  | deliverable
| 1.2.1 | Perform preliminary Market Analysis | Okan | 2025-10-13 | 2025-10-14 | 1.1.5 | task
| 1.2.2 | Create Financial Estimates | Okan | 2025-10-14 | 2025-10-16 | 1.2.1 | task
| 1.2.3 | Perform Detailed Market Analysis | Okan | 2025-10-16 | 2025-10-17 | 1.2.2 | task
| 1.2.4 | Approve Market Analysis Report | Justin | 2025-10-17 | 2025-10-18 | 1.2.3 | task
| 1.3 | Overall Product Concept |  | 2025-10-13 | 2025-10-28 |  | deliverable
| 1.3.1 | Creating Requirements List | Ahmad | 2025-10-13 | 2025-10-14 | 1.1.5 | task
| 1.3.2 | Abstract the Problem and Identify Functions | Justin, Ahmad | 2025-10-13 | 2025-10-15 | 1.3.1 | task
| 1.3.3 | Approve Key Functions | Wasim | 2025-10-15 | 2025-10-16 | 1.3.2 | task
| 1.3.4 | Developing Working Structures and Morphological Box | Justin, Ahmad, Abhinav, Wasim | 2025-10-15 | 2025-10-16 | 1.3.3 | task
| 1.3.4.1 | Adjust Solution according to Market Analysis | Ahmad | 2025-10-17 | 2025-10-18 | 1.2.3, 1.3.4 | task
| 1.3.4.2 | Adjust Solution according to FMEA | Wasim | 2025-10-25 | 2025-10-26 | 1.6.3, 1.3.4 | task
| 1.3.5 | Drawing Concept Sketch | Ahmad | 2025-10-18 | 2025-10-22 | 1.3.4.1 | task
| 1.3.6 | Compile preliminary bill of materials | Justin | 2025-10-26 | 2025-10-27 | 1.3.4.2 | task
| 1.3.7 | Approve Overall Product Concept | Wasim | 2025-10-27 | 2025-10-28 | 1.3.6 | task
| 1.4 | Functional Structure |  | 2025-10-18 | 2025-10-27 |  | deliverable
| 1.4.1 | Create preliminary product FSD | Justin | 2025-10-18 | 2025-10-21 | 1.3.4.1 | task
| 1.4.2 | Adjust FSD according to FMEA | Justin | 2025-10-25 | 2025-10-26 | 1.6.3 | task
| 1.4.3 | Approve product FSD | Abhinav | 2025-10-26 | 2025-10-27 | 1.4.2 | task
| 1.5 | Human Machine Interface |  | 2025-10-21 | 2025-10-27 |  | deliverable
| 1.5.1 | Create table of I/O Interactions | Abhinav | 2025-10-21 | 2025-10-22 | 1.4.1 | task
| 1.5.2 | Define and Arrange Control Elements | Abhinav | 2025-10-22 | 2025-10-23 | 1.5.1, 1.3.5 | task
| 1.5.3 | Adjust HMI according to FMEA | Abhinav | 2025-10-25 | 2025-10-26 | 1.6.3 | task
| 1.5.4 | Approve HMI | Ahmad | 2025-10-26 | 2025-10-27 | 1.5.3 | task
| 1.6 | D-FMEA |  | 2025-10-22 | 2025-10-27 |  | deliverable
| 1.6.1 | Create Basis for Failure Analysis | Wasim | 2025-10-22 | 2025-10-23 | 1.5.2 | task
| 1.6.2 | Identify Preliminary Failure Modes | Wasim | 2025-10-23 | 2025-10-24 | 1.6.1 | task
| 1.6.3 | Create Draft of D-FMEA Table | Ahmad, Wasim | 2025-10-23 | 2025-10-24 | 1.6.2 | task
| 1.6.4 | Create Final D-FMEA Report | Justin, Abhinav | 2025-10-25 | 2025-10-26 | 1.6.3 | task
| 1.6.5 | Approve D-FMEA Report | Okan | 2025-10-26 | 2025-10-27 | 1.6.4 | task
| 1.7 | Concept Design Close-out | Justin, Okan, Ahmad, Abhinav, Wasim | 2025-10-28 | 2025-10-28 | 1.6.5, 1.2.4, 1.5.4, 1.4.3, 1.3.7 | milestone
| 2 | Product Design |  | 2025-10-29 | 2025-12-02 |  | phase
| 2.1 | Complete 3D Model |  | 2025-10-29 | 2025-12-02 |  | deliverable
| 2.1.1 | Design the Housing and Internal Structure | Ahmad | 2025-10-29 | 2025-11-19 | 1.7 | task
| 2.1.2 | Approve of General Structure | Wasim | 2025-11-19 | 2025-11-20 | 2.1.1 | task
| 2.1.3 | Integrate PCB and Connectors into 3D Model | Ahmad, Wasim | 2025-11-20 | 2025-11-22 | 2.3.5, 2.1.2 | task
| 2.1.4 | Perform Assembly & Interference Check | Ahmad | 2025-11-22 | 2025-11-24 | 2.1.3 | task
| 2.1.5 | Adjust 3D Model based on results of Assembly test | Ahmad | 2025-11-24 | 2025-11-25 | 2.1.4 | task
| 2.1.6 | Assign Material | Ahmad | 2025-11-25 | 2025-11-26 | 2.1.5 | task
| 2.1.7 | Adjust 3D Model According to Manufacturability | Ahmad, Wasim | 2025-11-28 | 2025-11-27 | 2.1.6, 2.4.3 | task
| 2.1.8 | Adjust 3D Model According to Part Availability | Okan, Ahmad | 2025-11-29 | 2025-11-28 | 2.1.7, 2.5.2 | task
| 2.1.9 | Approve 3D Model | Wasim | 2025-12-01 | 2025-12-02 | 2.1.8 | task
| 2.2 | Measurement Chain |  | 2025-10-29 | 2025-11-11 |  | deliverable
| 2.2.1 | Identify necessary Signal Conditioning | Justin | 2025-10-29 | 2025-10-30 | 1.7 | task
| 2.2.2 | Design Schematics for Signal Condition | Justin | 2025-10-30 | 2025-11-03 | 2.2.1 | task
| 2.2.3 | Adjust Signal Conditioning according to Feedback from Circuit Design | Justin, Wasim | 2025-11-06 | 2025-11-08 | 2.3.3 | task
| 2.2.4 | Create detailed Measurement Chain FSD | Justin | 2025-11-08 | 2025-11-10 | 2.2.3 | task
| 2.2.5 | Approve the Measurement Chain Design | Abhinav | 2025-11-10 | 2025-11-11 | 2.2.4 | task
| 2.3 | Circuit Diagram |  | 2025-10-29 | 2025-12-02 |  | deliverable
| 2.3.1 | Draw Electrical System Block Diagram | Wasim | 2025-10-29 | 2025-10-31 | 1.7 | task
| 2.3.2 | Create Draft Circuit Schematic | Wasim | 2025-10-31 | 2025-11-04 | 2.3.1 | task
| 2.3.3 | Integrate Signal Processing Schematics | Justin, Wasim | 2025-11-04 | 2025-11-06 | 2.3.2, 2.2.2 | task
| 2.3.4 | Design Detailed Circuit Schematic | Abhinav, Wasim | 2025-11-06 | 2025-11-11 | 2.3.3 | task
| 2.3.5 | Design PCB | Abhinav, Wasim | 2025-11-11 | 2025-11-19 | 2.3.4, 2.2.3 | task
| 2.3.6 | Perform Electrical Safety Checks | Wasim | 2025-11-19 | 2025-11-21 | 2.3.5 | task
| 2.3.7 | Adjust PCB according to Manufacturability | Wasim | 2025-11-27 | 2025-11-28 | 2.4.3, 2.3.6 | task
| 2.3.8 | Adjust PCB according to Availability | Wasim | 2025-11-28 | 2025-11-29 | 2.5.2 | task
| 2.3.9 | Create Final Electrical Documentation Package | Wasim | 2025-11-29 | 2025-12-01 | 2.3.7, 2.3.8 | task
| 2.3.10 | Approve Final Circuit Diagram | Justin | 2025-12-01 | 2025-12-02 | 2.3.9, 2.2.5 | task
| 2.4 | Technology Selection for “Make” Parts |  | 2025-11-21 | 2025-12-02 |  | deliverable
| 2.4.1 | Identify all necessary “make” parts | Justin | 2025-11-21 | 2025-11-22 | 2.3.5, 2.1.3 | task
| 2.4.2 | Approve list of “Make” + “Buy” parts | Okan | 2025-11-23 | 2025-11-24 | 2.4.1, 2.5.1 | task
| 2.4.3 | Assess Manufacturability of Parts | Wasim | 2025-11-24 | 2025-11-27 | 2.4.2 | task
| 2.4.4 | Select Manufacturing Process and Materials for each part | Wasim | 2025-11-26 | 2025-11-27 | 2.4.3 | task
| 2.4.5 | Approve of material and manufacturing processes of “make” parts | Justin | 2025-11-27 | 2025-11-28 | 2.4.4 | task
| 2.4.6 | Define the Assembly Technology (Area by Area) | Justin, Wasim | 2025-11-28 | 2025-12-01 | 2.4.5 | task
| 2.4.7 | Approve Manufacturing and Assembly Guide Package | Okan | 2025-12-01 | 2025-12-02 | 2.4.6 | task
| 2.5 | Requirements Manual for “Buy” Parts |  | 2025-11-21 | 2025-12-02 |  | deliverable
| 2.5.1 | Identify all necessary “buy” parts | Okan | 2025-11-21 | 2025-11-22 | 2.1.3, 2.3.5 | task
| 2.5.2 | Assess availability of "buy" Parts | Okan | 2025-11-24 | 2025-11-27 | 2.4.2 | task
| 2.5.3 | Create part requirements sheets for each “buy” part | Okan, Ahmad | 2025-11-27 | 2025-12-01 | 2.5.2 | task
| 2.5.4 | Approve requirement sheets | Justin | 2025-12-01 | 2025-12-02 | 2.5.3 | task
| 2.6 | Product Design Close-out | Justin, Okan, Ahmad, Abhinav, Wasim | 2025-12-02 | 2025-12-02 | 2.5.4, 2.4.7, 2.3.10, 2.1.9 | milestone
| 3 | Project Documentation |  | 2025-10-29 | 2026-01-12 |  | phase
| 3.1 | Technical Drawings for Main Assembly |  | 2025-12-03 | 2026-01-04 |  | deliverable
| 3.1.1 | Create Assembly Drawing with Section and Detail Views | Ahmad | 2025-12-03 | 2025-12-17 | 2.6 | task
| 3.1.2 | Verify drawings for electrical components | Wasim | 2025-12-17 | 2025-12-19 | 3.1.1, 3.4.3 | task
| 3.1.3 | Verify Compliance with DIN 406 Drawing Standards | Abhinav | 2025-12-20 | 2025-12-22 | 3.1.2 | task
| 3.1.4 | Approval of technical drawing | Wasim | 2026-01-03 | 2026-01-04 | 3.1.3 | task
| 3.2 | Program Flow Chart |  | 2025-12-03 | 2025-12-18 |  | deliverable
| 3.2.1 | Draw Main structural flowchart | Abhinav | 2025-12-03 | 2025-12-07 | 2.6 | task
| 3.2.2 | Draw User interaction flowchart | Abhinav | 2025-12-07 | 2025-12-09 | 3.2.1 | task
| 3.2.3 | Draw Calibration menu flowchart | Abhinav | 2025-12-08 | 2025-12-10 | 3.2.2 | task
| 3.2.4 | Draw Data handling flowchart | Abhinav | 2025-12-10 | 2025-12-11 | 3.2.3 | task
| 3.2.5 | Draw Error and Internal Interrupt handling flowchart | Abhinav | 2025-12-11 | 2025-12-12 | 3.2.4 | task
| 3.2.6 | Approve program flowcharts | Ahmad | 2025-12-19 | 2025-12-18 | 3.2.5 | task
| 3.3 | Bill of Material |  | 2025-12-03 | 2026-01-04 |  | deliverable
| 3.3.1 | Create master BOM spreadsheet | Justin | 2025-12-03 | 2025-12-04 | 2.6 | task
| 3.3.2 | Itemize all Mechanical Components |  | 2025-12-04 | 2025-12-10 |  | tasks group
| 3.3.2.1 | Identify norm spec for each standard mechanical component | Justin | 2025-12-04 | 2025-12-07 | 3.3.1 | task
| 3.3.2.2 | Verify all specifications of all mechanical components | Wasim | 2025-12-07 | 2025-12-10 | 3.3.2.1 | task
| 3.3.3 | Itemize all Electrical Components |  | 2025-12-10 | 2025-12-16 |  | tasks group
| 3.3.3.1 | Add technical specs for all electrical components | Justin | 2025-12-10 | 2025-12-13 | 3.3.2.2 | task
| 3.3.3.2 | Verify all specifications of all electrical components | Ahmad | 2025-12-13 | 2025-12-16 | 3.3.3.1 | task
| 3.3.4 | Add cost to all components | Justin | 2025-12-16 | 2025-12-19 | 3.3.3.2 | task
| 3.3.5 | Verify Part Numbers according to Drawings | Justin | 2025-12-20 | 2025-12-22 | 3.1.2 | task
| 3.3.6 | Approve final BOM | Abhinav | 2026-01-03 | 2026-01-04 | 3.3.5 | task
| 3.4 | Production Planning |  | 2025-12-03 | 2026-01-08 |  | deliverable
| 3.4.1 | Estimate Number of Required Machines | Wasim | 2025-12-03 | 2025-12-05 | 2.6 | task
| 3.4.2 | Estimate Manufacturing and Assembly Time per Part | Wasim | 2025-12-05 | 2025-12-11 | 3.4.1 | task
| 3.4.3 | Create Assembly Sequence and Flowchart | Abhinav, Wasim | 2025-12-11 | 2025-12-15 | 3.4.2 | task
| 3.4.4 | Estimate Workforce Requirements | Wasim | 2025-12-15 | 2025-12-17 | 3.4.3 | task
| 3.4.5 | Optimize Assembly Sequence Costs | Abhinav, Wasim | 2025-12-20 | 2025-12-23 | 3.5.3 | task
| 3.4.6 | Approve of Assembly Sequence and Flowchart | Justin | 2026-01-03 | 2026-01-04 | 3.4.5 | task
| 3.4.7 | Create Production Planning Summary | Wasim | 2026-01-04 | 2026-01-07 | 3.4.6 | task
| 3.4.8 | Approve Production Plan | Okan | 2026-01-07 | 2026-01-08 | 3.4.7 | task
| 3.5 | Cost Calculation |  | 2025-12-05 | 2026-01-06 |  | deliverable
| 3.5.1 | Estimate Fixed Costs | Okan | 2025-12-05 | 2025-12-11 | 3.4.1 | task
| 3.5.2 | Estimate Variable Costs |  | 2025-12-11 | 2025-12-16 | 3.5.1 | tasks group
| 3.5.2.1 | Perform Initial Variable Cost Estimation | Okan | 2025-12-11 | 2025-12-16 | 3.4.2 | task
| 3.5.2.2 | Perform Final Variable Cost Estimate | Okan | 2025-12-19 | 2025-12-22 | 3.5.2.1, 3.4.4, 3.3.4 | task
| 3.5.3 | Estimate Overheads and Miscellaneous | Okan | 2025-12-16 | 2025-12-19 | 3.5.2.1 | task
| 3.5.4 | Summary Costs and Revenue Projection | Okan | 2026-01-03 | 2026-01-05 | 3.5.2.2, 3.5.3 | task
| 3.5.5 | Approve Cost Calculation Report | Justin | 2026-01-05 | 2026-01-06 | 3.5.4 | task
| 3.6 | Specification sheet |  | 2025-10-29 | 2026-01-04 |  | deliverable
| 3.6.1 | Outline Functional specifications | Abhinav | 2025-10-29 | 2025-10-31 | 1.7 | task
| 3.6.2 | Outline Physical and Mechanical Specifications | Ahmad, Abhinav | 2025-11-20 | 2025-11-22 | 2.1.2, 3.6.1 | task
| 3.6.3 | Outline Electrical Specifications | Abhinav, Wasim | 2025-11-23 | 2025-11-27 |  | task
| 3.6.4 | Adjust Specification on Final Design | Abhinav | 2025-12-12 | 2025-12-17 | 3.6.3, 3.6.2, 2.6 | task
| 3.6.5 | Approve specifications sheet | Justin | 2026-01-03 | 2026-01-04 | 3.6.4 | task
| 3.7 | User manual |  | 2025-11-21 | 2026-01-04 |  | deliverable
| 3.7.1 | Write Safety Disclaimers | Justin | 2025-11-21 | 2025-11-23 | 2.3.6 | task
| 3.7.2 | Write Functional Instructions | Okan | 2025-12-10 | 2025-12-15 | 3.2.2, 3.7.1 | task
| 3.7.3 | Explain troubleshooting steps | Abhinav | 2025-12-17 | 2025-12-23 | 3.7.2 | task
| 3.7.4 | Approve user manual | Ahmad | 2026-01-03 | 2026-01-04 | 3.7.3 | task
| 3.8 | Interactive brochure |  | 2025-11-11 | 2026-01-12 |  | deliverable
| 3.8.1 | Create first draft of Brochure | Justin, Ahmad, Abhinav | 2025-11-11 | 2025-12-01 | 1.7 | task
| 3.8.2 | Create Interactive Media for brochure | Justin, Ahmad, Abhinav | 2025-12-17 | 2025-12-22 | 3.8.1, 2.1.9 | task
| 3.8.3 | Design Final Brochure | Justin, Ahmad, Abhinav | 2026-01-04 | 2026-01-11 | 3.8.2 | task
| 3.8.4 | Approve brochure | Okan, Wasim | 2026-01-11 | 2026-01-12 | 3.8.3 | task
| 3.9 | Project Documentation Closeout | Justin, Okan, Ahmad, Abhinav, Wasim | 2026-01-12 | 2026-01-12 | 3.1.4, 3.5.5, 3.4.8, 3.3.6, 3.6.5, 3.7.4, 3.8.4, 3.2.6 | milestone
| 4 | Project Close-out | Justin, Okan, Ahmad, Abhinav, Wasim | 2026-01-13 | 2026-01-13 | 3.9 | milestone